## Slide 1: Partnership refresh and refocus 2017-2019
Birmingham South
Community Safety Partnership

## Slide 2: Proposal
To review and refresh the Birmingham South Community Safety Partnership, including:
  Its purpose, outcomes and functions
  Its membership and stakeholders
  Re-drafting its terms of reference, including defining the linkages to other groups and themes
Draft a “partnership agreement” which all partners can contribute and sign up to and which will underpin how the partnership operates and functions
Ensure that we have an effective partnership of equal partners and provide the groundwork before refreshing the priorities and activity for 2017-2019
Applicable to 2017-2019

## Slide 3: Timetable
September-November
  Current partner and stakeholder engagement
    Review and refresh the partnership’s purpose, outcomes and functions
  Draft and agree a new Terms of Reference
November-January
  Draft and agree a “partnership agreement”
January-March
  Draft and agree partnership priorities
  Draft partnership plan
March-May
  Agree partnership plan
  Commission activity to deliver the plan
May+
  Reporting, monitoring, adjusting
  Emerging issues

## Slide 4: What’s the ask of you?
Provide your views and input about:
  Purpose and outcomes for the partnership, including what outcomes your organisation might want from the partnership
  What level of involvement your organisation/service would like to have between 2017 and 2019
  Who the best contact or representative for your organisation/service might be(if not you)
  What offer or commitment your organisation/service could make to the partnership
  What you think the partnership needs to add, change or do differently

## Slide 5: Local overlaps and linkages

## Slide 6: Timetable and cycle 2017-19
Refresh the partnership; Analyse and define problems or opportunities
Assess profile and need, services and assets, tools and powers
Plan, define outputs and measurable outcomes
Gap analysis
Implement plan and commission activity
Monitoring and review
Outputs
Framed by BCSP priorities and plan, as well as LCSP outcomes
Formulate local strategy (how we will deliver outcomes)
Design and develop plan (what we will do and when)
Sept' 2016-Jan' 2017
Jan-Mar 2017
Agree plan
Establish project groups
Agree leads
Establish task and finish groups
Establish working groups
Issue grants schemes
"Procure" provision, services or support
March-May 2017
Lessons being learned
Adjust plans and activity as appropriate
May 2017-March 2019
Highlight reports
Outcomes
Refresh partnership purpose, outcomes, members and terms of reference
Agree partnership agreement